## Cover
Goldfields Gas Pipeline Access Arrangment 2025-29
End of equipment life NPV Analysis
2023-12-01

## Sys
Model System: lists, values, formatting
Formatting
| Heading 1 | Heading 2 | Input | Calculation | Highlight | Explanatory text
Values
| Millions | 1000000
| Real WACC | 5.18%
NPV Set up
Options
| 1 | Option 1 - Defer to AA6
| 2 | Option 2 - Focus on control and cathodic protection systems
| 3 | Option 3 - Complete in AA5
| 4 | Option 4 - Complete over AA5 and AA6
5
6
Lists
| No. | Basis
| 1 | $FY2023
| 2 | $nominal
| 3 | $CY2023
4
5
6
7

## I¦Program
Inputs
1 | Option 1 - Defer to AA6
| Project Title | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34
| Re-life Program - Beyondie Meter Station EI&C Systems (R) | FY30: 0; FY31: 50000; FY32: 450000
| Re-life Program - Control System Upgrade - Wiluna Gold | FY30: 50000; FY31: 250000
| Re-life Program - Cosmos OT | FY31: 1150000
| Re-life Program - CP Data Loggers - GGP | FY33: 340899; FY34: 319719
| Re-life Program - Esperance MS - Station RTU Upgrade | FY33: 50000; FY34: 700000
| Re-life Program - Ilgarari EI&C | FY33: 1100000; FY34: 1050000
| Re-life Program - Jaguar OT | FY32: 50000; FY33: 1100000; FY34: 0
| Re-life Program - Jeedamya | FY31: 50000; FY32: 1400000
| Re-life Program - Kalgoorlie North MLV | FY31: 50000; FY32: 1550000
| Re-life Program - Kalgoorlie South - Station RTU Upgrade | FY30: 411841; FY31: 0
| Re-life Program - Kalgoorlie South CPU Upgrade | FY30: 0; FY31: 50000; FY32: 500000
| Re-life Program - Kalgoorlie West MLV | FY30: 0; FY31: 50000; FY32: 1000000
| Re-life Program - Kambalda MS - Station RTU Upgrade | FY30: 433239
| Re-life Program - Leinster MS EI&C | FY30: 526937; FY31: 382513
| Re-life Program - Leinster SS | FY30: 200000; FY31: 800000; FY32: 1500000
| Re-life Program - Leonora MLV | FY30: 195000; FY31: 555000
| Re-life Program - Leonora MS | FY30: 60000; FY33: 1750000
| Re-life Program - Marymia - CPU Upgrade | FY30: 50000; FY31: 200000; FY33: 0
| Re-life Program - Mt Keith MLV (SS) | FY30: 195000; FY31: 1405000; FY33: 0
| Re-life program - Mt Keith MS - Mech | FY30: 567000; FY31: 1100000; FY33: 0
| Re-life Program - Mt Keith MS EI&C | FY30: 742026; FY31: 1450655; FY33: 0
| Re-life Program - Neds Creek EI&C | FY31: 1514367; FY33: 0
| Re-life Program - Neds Creek SS | FY33: 50000; FY34: 1100000
| Re-life Program - Newman Delivery | FY31: 50000; FY32: 200000; FY33: 1350000
| Re-life Program - Newman SS | FY31: 100000; FY32: 1750000
| Re-life Program - Paraburdoo - Station RTU Upgrade | FY30: 1147121; FY31: 750451
| Re-life Program - Paraburdoo SS (R) | FY30: 0; FY31: 0; FY33: 50000; FY34: 1400000
| Re-life Program - Parkeston MS Station RTU Upgrade | FY30: 0; FY31: 750000
| Re-life Program - Three Rivers MLV | FY30: 50000; FY31: 1550000
| Re-life Program - Turee Creek SS | FY30: 0; FY32: 50000; FY33: 1100000
| Re-life Program - Wyloo West - Station RTU Upgrade | FY30: 763233; FY31: 635657
| Re-life Program - Wyloo West SS | FY33: 50000; FY34: 1100000
| Re-life Program - Yarnima MS | FY30: 50000; FY31: 550000
| Re-life Program - Yarraloola CPU Upgrade | FY31: 50000; FY32: 200000
| Re-life Program -Boonamichi Well MS (R) | FY33: 50000; FY34: 1100000
| Reactive repairs | FY25: 413456.58; FY26: 413456.58; FY27: 413456.58; FY28: 413456.58; FY29: 413456.58
| Total | 0 | 413456.58 | 413456.58 | 413456.58 | 413456.58 | 413456.58 | 5441397 | 13493643 | 8650000 | 6990899 | 6769719
2 | Option 2 - Focus on control and cathodic protection systems
| Project Title | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34
| Re-life Program - Beyondie Meter Station EI&C Systems (R) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 450000 | 0 | 0
| Re-life Program - Control System Upgrade - Wiluna Gold | 0 | 50000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Component | Cost
| Re-life Program - Cosmos OT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150000 | 0 | 0 | 0 | Actuator cost | 300000
| Re-life Program - CP Data Loggers - GGP | 0 | 340899 | 319719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Solar power | 300000
| Re-life Program - Esperance MS - Station RTU Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 700000 | Additional mobilisation / rework premium | 150%
| Re-life Program - Ilgarari EI&C | 0 | 1100000 | 750000 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 0
| Re-life Program - Jaguar OT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 1100000 | 0
| Re-life Program - Jeedamya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 1400000 | 0 | 0
| Re-life Program - Kalgoorlie North MLV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 1550000 | 0 | 0
| Re-life Program - Kalgoorlie South - Station RTU Upgrade | 411841 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Re-life Program - Kalgoorlie South CPU Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 500000 | 0 | 0
| Re-life Program - Kalgoorlie West MLV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 1000000 | 0 | 0
| Re-life Program - Kambalda MS - Station RTU Upgrade | 433239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Leinster MS EI&C | 526937 | 382513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Leinster SS | 200000 | 800000 | 900000 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0
| Re-life Program - Leonora MLV | 195000 | 555000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Re-life Program - Leonora MS | 60000 | 0 | 1150000 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 0
| Re-life Program - Marymia - CPU Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 200000 | 0 | 0 | 0
| Re-life Program - Mt Keith MLV (SS) | 195000 | 805000 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 0
| Re-life program - Mt Keith MS - Mech | 567000 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Mt Keith MS EI&C | 742026 | 1450655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Neds Creek EI&C | 0 | 1214367 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0 | 0
| Re-life Program - Neds Creek SS | 0 | 0 | 0 | 50000 | 800000 | 0 | 0 | 0 | 0 | 450000 | 0
| Re-life Program - Newman Delivery | 0 | 50000 | 200000 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Newman SS | 0 | 100000 | 1150000 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0
| Re-life Program - Paraburdoo - Station RTU Upgrade | 1147121 | 450451 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0
| Re-life Program - Paraburdoo SS (R) | 0 | 0 | 0 | 50000 | 1100000 | 0 | 0 | 0 | 0 | 450000 | 0
| Re-life Program - Parkeston MS Station RTU Upgrade | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Three Rivers MLV | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 1550000 | 0 | 0 | 0
| Re-life Program - Turee Creek SS | 0 | 0 | 50000 | 800000 | 0 | 0 | 0 | 0 | 0 | 450000 | 0
| Re-life Program - Wyloo West - Station RTU Upgrade | 763233 | 635657 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| Re-life Program - Wyloo West SS | 0 | 0 | 0 | 0 | 50000 | 800000 | 0 | 0 | 0 | 450000 | 0
| Re-life Program - Yarnima MS | 0 | 50000 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Yarraloola CPU Upgrade | 0 | 0 | 50000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program -Boonamichi Well MS (R) | 0 | 0 | 0 | 0 | 50000 | 800000 | 0 | 0 | 0 | 0 | 450000
| Total | 5241397 | 9834542 | 5369719 | 2450000 | 2000000 | 1600000 | 100000 | 5850000 | 6300000 | 3850000 | 1150000
3 | Option 3 - Complete in AA5
| Project Title | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34
| Re-life Program - Beyondie Meter Station EI&C Systems (R) | 0 | 0 | 0 | 0 | 50000 | 450000 | 0 |  |  | 0 | 0
| Re-life Program - Control System Upgrade - Wiluna Gold | 0 | 50000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Cosmos OT | 0 | 0 | 0 | 1150000 | 0 | 0 | 0 |  | 0 | 0 | 0
| Re-life Program - CP Data Loggers - GGP | 0 | 340899 | 319719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Esperance MS - Station RTU Upgrade | 0 | 0 | 50000 | 700000 |  | 0 | 0 | 0 | 0
| Re-life Program - Ilgarari EI&C | 0 | 1100000 | 1050000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Jaguar OT | 0 | 0 | 0 | 0 | 50000 | 1100000 |  | 0 |  |  | 0
| Re-life Program - Jeedamya | 0 | 0 | 0 | 50000 | 1400000 | 0 | 0 |  |  | 0 | 0
| Re-life Program - Kalgoorlie North MLV | 0 | 0 | 0 | 50000 | 1550000 | 0 | 0 |  |  | 0 | 0
| Re-life Program - Kalgoorlie South - Station RTU Upgrade | 411841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Kalgoorlie South CPU Upgrade | 0 | 0 | 0 | 0 | 50000 | 500000 | 0 |  |  | 0 | 0
| Re-life Program - Kalgoorlie West MLV | 0 | 0 | 0 | 50000 | 1000000 |  | 0 |  |  | 0 | 0
| Re-life Program - Kambalda MS - Station RTU Upgrade | 433239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Leinster MS EI&C | 526937 | 382513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Leinster SS | 200000 | 800000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Leonora MLV | 195000 | 555000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Leonora MS | 60000 | 0 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Marymia - CPU Upgrade | 0 | 0 | 0 | 0 | 50000 | 200000 |  |  | 0 | 0 | 0
| Re-life Program - Mt Keith MLV (SS) | 195000 | 1405000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life program - Mt Keith MS - Mech | 567000 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Mt Keith MS EI&C | 742026 | 1450655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Neds Creek EI&C | 0 | 1514367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Neds Creek SS | 0 | 0 | 0 | 50000 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Newman Delivery | 0 | 50000 | 200000 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Newman SS | 0 | 100000 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Paraburdoo - Station RTU Upgrade | 1147121 | 750451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Paraburdoo SS (R) | 0 | 0 | 0 | 50000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Parkeston MS Station RTU Upgrade | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Three Rivers MLV | 0 | 0 | 0 | 0 | 50000 | 1550000 |  |  | 0 | 0 | 0
| Re-life Program - Turee Creek SS | 0 | 0 | 50000 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Wyloo West - Station RTU Upgrade | 763233 | 635657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Wyloo West SS | 0 | 0 | 0 | 0 | 50000 | 1100000 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Yarnima MS | 0 | 50000 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Yarraloola CPU Upgrade | 0 | 0 | 50000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program -Boonamichi Well MS (R) | 0 | 0 | 0 | 0 | 50000 | 1100000 | 0 | 0 | 0 | 0 | 0
| Total | 5241397 | 11034542 | 7519719 | 4750000 | 6800000 | 6000000 | 0 | 0 | 0 | 0 | 0
4 | Option 4 - Complete over AA5 and AA6
| Project Title | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34
| Re-life Program - Beyondie Meter Station EI&C Systems (R) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 450000 | 0 | 0
| Re-life Program - Control System Upgrade - Wiluna Gold | 0 | 50000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Cosmos OT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150000 | 0 | 0 | 0
| Re-life Program - CP Data Loggers - GGP | 0 | 340899 | 319719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Esperance MS - Station RTU Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 700000
| Re-life Program - Ilgarari EI&C | 0 | 1100000 | 1050000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Jaguar OT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 1100000 | 0
| Re-life Program - Jeedamya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 1400000 | 0 | 0
| Re-life Program - Kalgoorlie North MLV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 1550000 | 0 | 0
| Re-life Program - Kalgoorlie South - Station RTU Upgrade | 411841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Kalgoorlie South CPU Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 500000 | 0 | 0
| Re-life Program - Kalgoorlie West MLV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 1000000 | 0 | 0
| Re-life Program - Kambalda MS - Station RTU Upgrade | 433239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Leinster MS EI&C | 526937 | 382513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Leinster SS | 200000 | 800000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Leonora MLV | 195000 | 555000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Leonora MS | 60000 | 0 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Marymia - CPU Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 200000 | 0 | 0 | 0
| Re-life Program - Mt Keith MLV (SS) | 195000 | 1405000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life program - Mt Keith MS - Mech | 567000 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Mt Keith MS EI&C | 742026 | 1450655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Neds Creek EI&C | 0 | 1514367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Neds Creek SS | 0 | 0 | 0 | 50000 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Newman Delivery | 0 | 50000 | 200000 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Newman SS | 0 | 100000 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Paraburdoo - Station RTU Upgrade | 1147121 | 750451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Paraburdoo SS (R) | 0 | 0 | 0 | 50000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Parkeston MS Station RTU Upgrade | 0 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Three Rivers MLV | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 1550000 | 0 | 0 | 0
| Re-life Program - Turee Creek SS | 0 | 0 | 50000 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Wyloo West - Station RTU Upgrade | 763233 | 635657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Wyloo West SS | 0 | 0 | 0 | 0 | 50000 | 1100000 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Yarnima MS | 0 | 50000 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program - Yarraloola CPU Upgrade | 0 | 0 | 50000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-life Program -Boonamichi Well MS (R) | 0 | 0 | 0 | 0 | 50000 | 1100000 | 0 | 0 | 0 | 0 | 0
| Total | 5241397 | 11034542 | 7469719 | 2750000 | 2600000 | 2200000 | 100000 | 3150000 | 4950000 | 1150000 | 700000

## C¦NPV
Calc
Capex (Financial year terms) |  |  | FY
| Option | Basis | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
1 | Option 1 - Defer to AA6 | $CY2023 |  | 0 | 413456.58 | 413456.58 | 413456.58 | 413456.58 | 413456.58 | 5441397 | 13493643 | 8650000 | 6990899 | 6769719 | 0
2 | Option 2 - Focus on control and cathodic protection systems | $CY2023 |  | 5241397 | 9834542 | 5369719 | 2450000 | 2000000 | 1600000 | 100000 | 5850000 | 6300000 | 3850000 | 1150000 | 0
3 | Option 3 - Complete in AA5 | $CY2023 |  | 5241397 | 11034542 | 7519719 | 4750000 | 6800000 | 6000000 | 0 | 0 | 0 | 0 | 0 | 0
4 | Option 4 - Complete over AA5 and AA6 | $CY2023 |  | 5241397 | 11034542 | 7469719 | 2750000 | 2600000 | 2200000 | 100000 | 3150000 | 4950000 | 1150000 | 700000 | 0
Capex (Calendar year terms) | bar: FY 2023 to FY 2035
| Option | Basis | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
1 | Option 1 - Defer to AA6 | $CY2023 | 0 | 206728.29 | 413456.58 | 413456.58 | 413456.58 | 413456.58 | 2927426.79 | 9467520 | 11071821.5 | 7820449.5 | 6880309 | 3384859.5 | 0
2 | Option 2 - Focus on control and cathodic protection systems | $CY2023 | 2620698.5 | 7537969.5 | 7602130.5 | 3909859.5 | 2225000 | 1800000 | 850000 | 2975000 | 6075000 | 5075000 | 2500000 | 575000 | 0
3 | Option 3 - Complete in AA5 | $CY2023 | 2620698.5 | 8137969.5 | 9277130.5 | 6134859.5 | 5775000 | 6400000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0
4 | Option 4 - Complete over AA5 and AA6 | $CY2023 | 2620698.5 | 8137969.5 | 9252130.5 | 5109859.5 | 2675000 | 2400000 | 1150000 | 1625000 | 4050000 | 3050000 | 925000 | 350000 | 0
Summary table | bar: CY 2023 to CY 2028
| Option | Basis | CY 2023: Present Value (period to 2035); CY 2024: AA4 capex; CY 2025: AA5 Capex; CY 2026: AA6 Capex; CY 2027: Total; CY 2028: Total (Check)
1 | Option 1 - Defer to AA6 | $CY2023 | CY 2023: 28.8452; CY 2024: 0.20673; CY 2025: 4.5813; CY 2026: 38.625; CY 2027: 43.4129; CY 2028: 0
2 | Option 2 - Focus on control and cathodic protection systems | $CY2023 | CY 2023: 35.0684; CY 2024: 10.1587; CY 2025: 16.387; CY 2026: 17.2; CY 2027: 43.7457; CY 2028: 0
3 | Option 3 - Complete in AA5 | $CY2023 | CY 2023: 35.9223; CY 2024: 10.7587; CY 2025: 30.587; CY 2026: 0; CY 2027: 41.3457; CY 2028: 0
4 | Option 4 - Complete over AA5 and AA6 | $CY2023 | CY 2023: 34.5521; CY 2024: 10.7587; CY 2025: 20.587; CY 2026: 10; CY 2027: 41.3457; CY 2028: 0