## Clarifications
ARC - Clarification / Information Register
As at 04 July 2025
Reference | Category | Section | Issue | Request | Request # | Date | ARC Response | Date | Status | Arc Response
3 | A | 4.6.1 Bridges | Clarification required on the tables within the Bridge section of the report (Tables 4-8 to 4-11). It appears that the two Type 2b - PSC Tee-roff bridges in the Non-Operational Network Group have been excluded from Table 4-9. | ARC to review Bridge Tables (4-8 to 4-11) and provided additional substantiation. | 1 | 2025-07-01 |  |  | Open | The area of these bridges is erroneously not shown in Tables 4-9 and 4-10 of the submission, a number of bridges have also been identified as missing from the submission. Corrected tables are included in tab "Section 4.6.1" of this workbook, resulting in an increase to the bridges construction replacement cost of $78m.
11 | A | 5.10.4 Summary of Rail Owners Project Costs | Clarification required to understand the apparent discrepancy between Tables 5-22 and 5-17. In particular, the OCC costs of the Signalling ad Control Systems appear to have not been transcribed properly | ARC requested to provide the basis and justification for the differing values as shown between Tables 5-17 and 5-22 | 1 | 2025-07-01 |  |  | Open | Total ORC shown in the submission is correct, however some figures shown in Table 5-22 were incorrect. The OCC Alternative Column should include the same costs as that shown in Table 5.17 in the submission and will be updated as such.
12 | A | 5.12.1 ORC Components by Network Group | Clarification required regarding the reported Owners costs that appear to be based on the Reconstruction Cost, not the Optimised Reconstruction cost as stated in the report. | ARC requested to provide calculations, and list of assumptions, used to determine the values in Table 5-25 | 1 | 2025-07-01 |  |  | Open | These Railway Owner Costs are based on the OCC, not the Replacement Cost. The Railway Owner Costs match those shown earlier in Table 5-22. For further information see response to Clarification 10 in the supporting document published on 11 July 2025.
15 | A | 6.2.5 Depreciated Optimised Replacement Cost - Right of Way | Clarification required to understand how Table 6-4 works in comparison to all other Depreciation Tables as the format differs. Uses a percent of Replacement Costs. | ARC to provide ORC by asset class breakdown of Table 6-4 | 1 | 2025-07-01 |  |  | Open | Table 6-4 in the submission shows similar information to other tables in this section, including Tables 6.6, 6.7 and 6.9. To enable easier interpretation the structure of this section will be rearranged and subtotals will be added to the tables. See example in tab "Section 6.2.5" of this workbook.
20 | A | 4.6.1 Bridges | Unable to reconcile bridge construction costs in table 4-11 due to: •Incomplete bridge deck area (m2) data in table 4-9 (e.g. Type 2b in Metro •Incomplete $/sqm data in table 4-10 (e.g. Type 2b in Metro) •Calculation errors (e.g. Type 1 in Midwest). | ARC requested to provide calculations and a list of any assumptions used to determine values in Table 4-11 | 1 | 2025-07-01 |  |  | Open | See additional information included as a response to Clarification #3 in tab "Section 4.6.1" of this workbook.
21 | A | 4.6.1 Bridges | Unexplained fluctuation in rates in table 4-10 | ARC requested to provide the rate build up used to determine the variable rates used in Table 4-10 | 1 | 2025-07-01 |  |  | Open | See additional information included as a response to Clarification #3 in tab "Section 4.6.1" of this workbook.
22 | A | 4.6.1 Bridges | Unable to review / validate Code route section quantities, specifications and costs due to lack of detail / aggregation | See request for additional information in Item 17 | 1 | 2025-07-01 |  |  | Open | Additional informaiton provided in tab "Section 4.6.1" of this workbook.
23 | A | 4.6.3 Culverts | Unexplained fluctuation in rates in table 4-16. | ARC requested to provide the rate build up used to determine the variable rates used in Table 4-16 | 1 | 2025-07-01 |  |  | Open | Total culvert replacement cost shown in Table 4-17 of the submission is correct, however some figures shown in Table 4-16 were incorrect. Corrected table is included in tab "Table 4-16" of this workbook, these corrected rates are a function of the location factors as outlined in Section 4.3 of the submission and the direct unit rates provided in the previous clarification register and published on 11th July 2025.
24 | A | 4.6.3 Culverts | Unable to review / validate Code route section quantities, specifications and costs due to lack of detail / aggregation | See request for additional information in Item 17 | 1 | 2025-07-01 |  |  | Open | Additional information provided in tab "Section 4.6.3" of this workbook. Additionally, some figures shown in Table 4-15 of the submission were incorrect, corrected table is included in tab "Section 4.6.3" of this workbook. The underlying calculations were correct so the total culvert replacement cost shown in Table 4-17 of the submission is correct.
47 | A | s5.10.1.2 | Table 5-19 Show how $18,368.2 is calculated by relating to earlier totals. Where are figures from col 1 taken from? Not clear that the last two columns are not related. | ARC are requested to provide the supporting calculations and or inputs used to arrive at the figures in column 1, and reference to earlier totals in the calculation of the $18,368.20 totals shown in Table 5-19 | 2 | 2025-07-03 |  |  | Open | The information preceding Table 5-19 in the submission, such as the totals in Table 5-17, already include the savings from alternative procurement. When an updated submission is provided, this will be broken down further to show how the OCC (Conventional Procurement) is derived, before stepping through the Alternative Procurement.

## Table 4-16
Table 4-16 Culvert Construction Replacement Cost Rates inc Location Factor ($'000s per metre)
Network Group | Construction Replacement Cost rate including location factor ($'000 per metre)
| 600 | 900 | 1200 | 1500 | 1800 | 2400 | 3000 | 3600
Metro | 896.805 | 0 | 1793.61 | 2242.0125 | 2690.415 | 3587.22 | 4484.025 | 0
EGR | 1087.8123 | 1671.8109 | 2353.7335 | 3095.4344 | 3427.0328 | 5009.6228 | 5707.9058 | 7292.6671
Midwest | 1165.8465 | 1748.7697 | 2331.693 | 2914.6162 | 3497.5395 | 4663.386 | 5829.2325 | 0
EBL | 1345.2075 | 2017.8112 | 2690.415 | 3363.0188 | 4035.6225 | 5380.83 | 6726.0375 | 8071.245
LBL | 1345.2075 | 2017.8113 | 2690.415 | 3363.0188 | 4035.6225 | 5380.83 | 6726.0375 | 8071.245
SWM | 1076.166 | 0 | 2152.332 | 2690.415 | 3228.498 | 4304.664 | 5380.83 | 0
Collie | 1076.166 | 1614.249 | 2152.332 | 2690.415 | 3228.498 | 4304.664 | 5380.83 | 0
MR | 1165.8465 | 1748.7697 | 2331.693 | 2914.6163 | 3497.5395 | 4663.386 | 5829.2325 | 6995.079
Central | 1076.166 | 1614.249 | 2152.332 | 2690.415 | 3228.498 | 4304.664 | 5380.83 | 6456.996
GSR | 1165.8465 | 1748.7697 | 2331.693 | 2914.6163 | 3497.5395 | 4663.386 | 5829.2325 | 6995.079
Lakes | 1165.8465 | 1748.7698 | 2331.693 | 2914.6163 | 3497.5395 | 4663.386 | 5829.2325 | 0
CBH Sidings | 1114.6304 | 1748.7697 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other | 1163.8612 | 0 | 0 | 2242.0125 | 0 | 0 | 0 | 0
Non-Operational | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Section 4.6.1
Table 4-8 Number of Bridges of each MEA by Network Group
Network group | MEA Type
| Type 1 - PCBC | Type 2a - PSC Plank | Type 2b - PSC Teeroff | Type 3 - Steel Composite | Type 4 - Steel Composite | Total
Metro | 0 | 0 | 1 | 4 | 1 | 6
EGR | 0 | 0 | 2 | 2 | 3 | 7
Midwest | 2 | 8 | 0 | 0 | 1 | 11
EBL | 0 | 1 | 0 | 0 | 0 | 1
LBL | 0 | 7 | 0 | 0 | 0 | 7
SWM | 1 | 34 | 7 | 8 | 0 | 50
Collie | 0 | 2 | 2 | 2 | 0 | 6
MR | 0 | 19 | 1 | 4 | 0 | 24
Central | 5 | 19 | 0 | 0 | 1 | 25
GSR | 3 | 34 | 2 | 1 | 2 | 42
Lakes | 1 | 2 | 0 | 0 | 0 | 3
CBH Sidings | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other | 0 | 0 | 2 | 0 | 0 | 2
Non-Operational | 7 | 36 | 1 | 1 | 1 | 46
Total | 19 | 162 | 18 | 22 | 9 | 230
Table 4-9 Total Bridge Deck Area (m2) of each MEA by Network Group
Network group | MEA Type
| Type 1 - PCBC (metric is bridge length (m)) | Type 2a - PSC Plank | Type 2b - PSC Teeroff | Type 3 - Steel Composite | Type 4 - Steel Composite
Metro | 0 | 0 | 720.9 | 1814.141 | 1442
EGR | 0 | 0 | 703.13 | 699.3736 | 1952.305
Midwest | 45.8 | 229.238 | 0 | 0 | 601.44
EBL | 0 | 27.81 | 0 | 0 | 0
LBL | 0 | 763.005 | 0 | 0 | 0
SWM | 13 | 2646.218 | 695.044 | 1644.97 | 0
Collie | 0 | 211.504 | 202.76 | 420.85 | 0
MR | 0 | 968.895 | 105.48 | 1539.65 | 0
Central | 25.166 | 1460.675 | 0 | 0 | 638.321
GSR | 25.8 | 2107.005 | 683.032 | 452.6 | 856.089
Lakes | 10.8 | 143.85 | 0 | 0 | 0
CBH Sidings | 0 | 0 | 0 | 0 | 0
Sidings & Other | 0 | 0 | 634.75 | 0 | 0
Non-Operational | 42.7 | 2779.4866 | 455.2928 | 70 | 533.4
Total | 163.266 | 11337.6866 | 4200.3888 | 6641.5846 | 6023.555
Table 4-10 Bridge Construction Replacement Cost Rate ($/m2) for each MEA Bridge Type, inc Location Factor
Network group | MEA Type
| Type 1 - PCBC (Rate is per metre length) | Type 2a - PSC Plank | Type 2b - PSC Teeroff | Type 3 - Steel Composite | Type 4 - Steel Composite
Metro | 0 | 0 | 13452.075 | 13452.075 | 12704.7375
EGR | 0 | 0 | 15595.815 | 15813.8315 | 13975.2113
Midwest | 612069.4125 | 16516.1587 | 0 | 0 | 57612.2479
EBL | 0 | 19057.1063 | 0 | 0 | 0
LBL | 0 | 19057.1063 | 0 | 0 | 0
SWM | 564987.15 | 15245.685 | 16142.49 | 16142.49 | 0
Collie | 0 | 15245.685 | 16142.49 | 16142.49 | 0
MR | 0 | 16516.1588 | 17487.6975 | 17487.6975 | 0
Central | 564987.15 | 15245.685 | 0 | 0 | 15245.685
GSR | 612069.4125 | 16516.1588 | 17487.6975 | 17487.6975 | 16516.1588
Lakes | 612069.4125 | 16516.1588 | 0 | 0 | 0
CBH Sidings | 0 | 0 | 0 | 0 | 0
Sidings & Other | 0 | 0 | 13452.075 | 0 | 0
Non-Operational | 612069.4125 | 16345.5563 | 17487.6975 | 17487.6975 | 15245.685
Note 1: The rate for the Type 4 Bridge in this section reflects the bridge's abnormal height
Table 4-11 Bridge Construction Replacement Cost ($ million)
Network group | MEA Type
| Type 1 - PCBC | Type 2a - PSC Plank | Type 2b - PSC Teeroff | Type 3 - Steel Composite | Type 4 - Steel Composite | Total
Metro | 0 | 0 | 9697600.8675 | 24403960.7926 | 18320231.475 | 52421793.1351
EGR | 0 | 0 | 10965885.367 | 11059776.2768 | 27283874.7994 | 49309536.4433
Midwest | 28032779.0925 | 3786131.1995 | 0 | 0 | 34650310.3619 | 66469220.654
EBL | 0 | 529978.1248 | 0 | 0 | 0 | 529978.1248
LBL | 0 | 14540667.3543 | 0 | 0 | 0 | 14540667.3543
SWM | 7344832.95 | 40343406.0693 | 11219740.8196 | 26553911.7753 | 0 | 85461891.6142
Collie | 0 | 3224523.3602 | 3273051.2724 | 6793566.9165 | 0 | 13291141.5491
MR | 0 | 16002423.6321 | 1844602.3323 | 26924933.4559 | 0 | 44771959.4203
Central | 14218466.6169 | 22268990.9374 | 0 | 0 | 9731640.8949 | 46219098.4492
GSR | 15791390.8425 | 34799629.067 | 11944656.9988 | 7914931.8885 | 14139301.8281 | 84589910.625
Lakes | 6610349.655 | 2375849.4362 | 0 | 0 | 0 | 8986199.0912
CBH Sidings | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other | 0 | 0 | 8538704.6062 | 0 | 0 | 8538704.6062
Non-Operational | 26135363.9138 | 45432254.6263 | 7962022.7603 | 1224138.825 | 8132048.379 | 88885828.5043
Total | 98133183.0707 | 183303853.8071 | 65446265.0242 | 104875219.9306 | 112257407.7384 | 564015929.5709
Section 4.6.1 Supporting Information - Bridge Inventory and Construction Replacement Cost ($ million) by Route Section
Route Section | Type 1 - PCBC |  | Type 2a - PSC Plank |  | Type 2b - PSC Teeroff |  | Type 3 - Steel Composite |  | Type 4 - Steel Composite |  | TOTAL Replacement Cost
| Length (m) | Replacement Cost ($) | Deck Area (m2) | Replacement Cost ($) | Deck Area (m2) | Replacement Cost ($) | Deck Area (m2) | Replacement Cost ($) | Deck Area (m2) | Replacement Cost ($)
Metro ¦ Kwinana West to Kwinana KBT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Kwinana North to Kwinana West | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Kwinana North to Kwinana | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Cockburn South to Kwinana North | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Cockburn East to Cockburn South | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Cockburn North to Cockburn East | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Cockburn North to Cockburn South | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Kenwick to Cockburn East | 0 | 0 | 0 | 0 | 0 | 0 | 1112.033 | 14959151.3185 | 0 | 0 | 14959151.3185
Metro ¦ Forrestfield to Kenwick | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Forrestfield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Forrestfield South to Kewdale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Woodbridge South to Forrestfield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1442 | 18320231.475 | 18320231.475
Metro ¦ Woodbridge West to Woodbridge South | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Midland to Woodbridge South | 0 | 0 | 0 | 0 | 720.9 | 9697600.8675 | 702.108 | 9444809.4741 | 0 | 0 | 19142410.3416
EGR ¦ Midland to Millendon Junction | 0 | 0 | 0 | 0 | 0 | 0 | 435.1216 | 6438617.2371 | 0 | 0 | 6438617.2371
EGR ¦ Millendon Junction to Toodyay West | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 667.645 | 9330479.915 | 9330479.915
EGR ¦ Toodyay West to Avon Yard | 0 | 0 | 0 | 0 | 564.001 | 8345682.1273 | 0 | 0 | 1284.66 | 17953394.8844 | 26299077.0117
EGR ¦ Avon Yard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EGR ¦ Avon Yard to West Merredin | 0 | 0 | 0 | 0 | 0 | 0 | 264.252 | 4621159.0398 | 0 | 0 | 4621159.0398
EGR ¦ West Merredin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EGR ¦ West Merredin to Merredin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EGR ¦ Merredin to Southern Cross | 0 | 0 | 0 | 0 | 139.129 | 2620203.2397 | 0 | 0 | 0 | 0 | 2620203.2397
EGR ¦ Southern Cross to Koolyanobbing East | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EGR ¦ Koolyanobbing East to Mount Walton | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EGR ¦ Mount Walton to West Kalgoorlie West | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EGR ¦ West Kalgoorlie West to West Kalgoorlie | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EGR ¦ West Kalgoorlie | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EGR ¦ West Kalgoorlie to Kalgoorlie | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EGR ¦ Kalgoorlie | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EGR ¦ Kalgoorlie to Parkeston (border) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Midwest ¦ Narngulu to Narngulu East | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Midwest ¦ Narngulu East to Mullewa | 42.4 | 25951743.09 | 61.95 | 1023176.0346 | 0 | 0 | 0 | 0 | 601.44 | 34650310.3619 | 61625229.4865
Midwest ¦ Mullewa to Tilley Junction | 3.4 | 2081036.0025 | 167.288 | 2762955.165 | 0 | 0 | 0 | 0 | 0 | 0 | 4843991.1675
Midwest ¦ Tilley Junction to Tilley | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Midwest ¦ Tilley to Morawa | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Midwest ¦ Morawa to Perenjori | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Midwest ¦ Perenjori to Maya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBL ¦ West Kalgoorlie West to West Kalgoorlie South | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBL ¦ West Kalgoorlie to West Kalgoorlie South | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBL ¦ West Kalgoorlie South to Hampton Intermodal Terminal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBL ¦ Hampton Intermodal Terminal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBL ¦ Hampton Intermodal Terminal to Hampton | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBL ¦ Hampton to Kambalda | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBL ¦ Kambalda to Redmine | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBL ¦ Kambalda to Salmon Gums | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBL ¦ Salmon Gums to Esperance | 0 | 0 | 27.81 | 529978.1248 | 0 | 0 | 0 | 0 | 0 | 0 | 529978.1248
EBL ¦ Esperance to Esperance Wharf | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBL ¦ Esperance Wharf | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LBL ¦ Kalgoorlie to Menzies | 0 | 0 | 700.005 | 13340069.6605 | 0 | 0 | 0 | 0 | 0 | 0 | 13340069.6605
LBL ¦ Menzies to Malcolm | 0 | 0 | 63 | 1200597.6937 | 0 | 0 | 0 | 0 | 0 | 0 | 1200597.6937
LBL ¦ Malcolm to Leonora | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LBL ¦ Leonora | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SWM ¦ Kwinana to Mundijong Junction | 0 | 0 | 802.542 | 12235302.5313 | 32 | 516559.68 | 0 | 0 | 0 | 0 | 12751862.2113
SWM ¦ Mundijong Junction to Pinjarra | 0 | 0 | 225.013 | 3430477.3189 | 102.4 | 1652990.976 | 162 | 2615083.38 | 0 | 0 | 7698551.6749
SWM ¦ Pinjarra to Pinjarra South | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SWM ¦ Pinjarra to Alumina Junction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SWM ¦ Alumina Junction to Pinjarra South | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SWM ¦ Pinjarra South to Wagerup North | 0 | 0 | 195.445 | 2979692.9048 | 0 | 0 | 292.06 | 4714575.6294 | 0 | 0 | 7694268.5342
SWM ¦ Wagerup North to Wagerup South | 0 | 0 | 13.904 | 211976.0042 | 0 | 0 | 0 | 0 | 0 | 0 | 211976.0042
SWM ¦ Wagerup South to Brunswick North | 0 | 0 | 139.846 | 2132048.0645 | 208.544 | 3366419.4346 | 0 | 0 | 0 | 0 | 5498467.4991
SWM ¦ Brunswick North to Brunswick Junction | 0 | 0 | 0 | 0 | 0 | 0 | 143.36 | 2314187.3664 | 0 | 0 | 2314187.3664
SWM ¦ Brunswick Junction to Picton Junction | 0 | 0 | 318.168 | 4850689.1051 | 0 | 0 | 445.55 | 7192286.4195 | 0 | 0 | 12042975.5246
SWM ¦ Picton Junction to Picton East | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SWM ¦ Picton Junction to Bunbury Inner Harbour | 0 | 0 | 581 | 8857742.985 | 240.8 | 3887111.592 | 0 | 0 | 0 | 0 | 12744854.577
SWM ¦ Picton Junction to Picton Container Terminal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SWM ¦ Picton Container Terminal to Bunbury Terminal | 13 | 7344832.95 | 0 | 0 | 0 | 0 | 249.55 | 4028358.3795 | 0 | 0 | 11373191.3295
SWM ¦ Picton Junction to Greenbushes | 0 | 0 | 370.3 | 5645477.1555 | 111.3 | 1796659.137 | 352.45 | 5689420.6005 | 0 | 0 | 13131556.893
Collie ¦ Brunswick North to Brunswick East | 0 | 0 | 0 | 0 | 0 | 0 | 168.85 | 2725659.4365 | 0 | 0 | 2725659.4365
Collie ¦ Brunswick Junction to Brunswick East | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collie ¦ Brunswick East to Worsley | 0 | 0 | 211.504 | 3224523.3602 | 34.76 | 561112.9524 | 0 | 0 | 0 | 0 | 3785636.3126
Collie ¦ Worsley to Worsley East | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collie ¦ Worsley East to Ewington Junction | 0 | 0 | 0 | 0 | 168 | 2711938.32 | 252 | 4067907.48 | 0 | 0 | 6779845.8
Collie ¦ Ewington Junction to Premier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collie ¦ Worsley East to Worsley North | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collie ¦ Worsley to Hamilton | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MR ¦ Millendon Junction to Watheroo | 0 | 0 | 617.048 | 10191262.7244 | 105.48 | 1844602.3323 | 830.2 | 14518286.4645 | 0 | 0 | 26554151.5212
MR ¦ Watheroo to Marchagee | 0 | 0 | 31.15 | 514478.3451 | 0 | 0 | 0 | 0 | 0 | 0 | 514478.3451
MR ¦ Marchagee to Dongara | 0 | 0 | 192.517 | 3179641.3341 | 0 | 0 | 261.45 | 4572158.5114 | 0 | 0 | 7751799.8454
MR ¦ Dongara to Narngulu | 0 | 0 | 128.18 | 2117041.2286 | 0 | 0 | 0 | 0 | 0 | 0 | 2117041.2286
MR ¦ Narngulu to Geraldton | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MR ¦ Dongara to Eneabba South | 0 | 0 | 0 | 0 | 0 | 0 | 448 | 7834488.48 | 0 | 0 | 7834488.48
Central ¦ Avon Yard to Goomalling | 0 | 0 | 901.5 | 13743985.0275 | 0 | 0 | 0 | 0 | 0 | 0 | 13743985.0275
Central ¦ Goomalling to McLevie | 7.4 | 4180904.91 | 124.135 | 1892523.1075 | 0 | 0 | 0 | 0 | 0 | 0 | 6073428.0175
Central ¦ Goomalling to Amery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central ¦ Amery to Mukinbudin | 0 | 0 | 74.906 | 1141993.2806 | 0 | 0 | 0 | 0 | 0 | 0 | 1141993.2806
Central ¦ Amery to Burakin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central ¦ Burakin to Kalannie | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central ¦ Burakin to Beacon | 0.266 | 150286.5819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150286.5819
Central ¦ Toodyay West to Miling | 17.5 | 9887275.125 | 360.134 | 5490489.5218 | 0 | 0 | 0 | 0 | 638.321 | 9731640.8949 | 25109405.5417
GSR ¦ Avon Yard to York | 7 | 4284485.8875 | 197.594 | 3263493.872 | 683.032 | 11944656.9988 | 0 | 0 | 856.089 | 14139301.8281 | 33631938.5865
GSR ¦ York to Brookton | 0 | 0 | 90.05 | 1487280.0954 | 0 | 0 | 452.6 | 7914931.8885 | 0 | 0 | 9402211.9839
GSR ¦ Brookton to Narrogin | 0 | 0 | 568.814 | 9394622.3232 | 0 | 0 | 0 | 0 | 0 | 0 | 9394622.3232
GSR ¦ Narrogin to Wagin | 0 | 0 | 510.78 | 8436123.5663 | 0 | 0 | 0 | 0 | 0 | 0 | 8436123.5663
GSR ¦ Wagin to Wagin South | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GSR ¦ Wagin South to Katanning | 10.4 | 6365521.89 | 220.15 | 3636032.3488 | 0 | 0 | 0 | 0 | 0 | 0 | 10001554.2388
GSR ¦ Katanning to Tambellup | 0 | 0 | 361.067 | 5963439.8914 | 0 | 0 | 0 | 0 | 0 | 0 | 5963439.8914
GSR ¦ Tambellup to Redmond | 8.4 | 5141383.065 | 158.55 | 2618636.9698 | 0 | 0 | 0 | 0 | 0 | 0 | 7760020.0348
GSR ¦ Redmond to Albany | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lakes ¦ Wagin East to Wagin South | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lakes ¦ Wagin to Lake Grace | 10.8 | 6610349.655 | 143.85 | 2375849.4362 | 0 | 0 | 0 | 0 | 0 | 0 | 8986199.0912
Lakes ¦ Lake Grace to Newdegate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lakes ¦ Lake Grace to Hyden | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CBH Sidings ¦ CBH SG Sidings (all) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CBH Sidings ¦ CBH NG Sidings (all) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ Cockburn North to Robb Jetty (SG) | 0 | 0 | 0 | 0 | 634.75 | 8538704.6062 | 0 | 0 | 0 | 0 | 8538704.6062
Sidings & Other ¦ SG Siding - Esperance Industrial Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ SG Siding - West Kalgoorlie Industrial Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ SG Siding - Kewdale North Grid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ SG Siding - Kewdale BP Loading Depot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ Cockburn North to Robb Jetty (NG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ Redmond to Mirrambeena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ NG Siding - Kwinana to Kwinana Alcoa | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ NG Siding - Kwinana to Kwinana West | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ NG Siding - Kwinana West to Kwinana KBT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ NG Siding - Extension Hill Siding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ NG Siding - Tilley Siding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ DG Siding - Kwinana West to Kwinana FPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ DG Siding - Kwinana FPA to Kwinana CBH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Operational ¦ Greenbushes to Lambert | 0 | 0 | 94.15 | 1435381.2427 | 0 | 0 | 0 | 0 | 533.4 | 8132048.379 | 9567429.6217
Non-Operational ¦ Boyanup to Capel | 0 | 0 | 279.0866 | 4254866.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 4254866.3913
Non-Operational ¦ York to Quairading | 3.7 | 2264656.8262 | 1068.9 | 17654122.0879 | 0 | 0 | 0 | 0 | 0 | 0 | 19918778.9141
Non-Operational ¦ Narrogin to West Merredin | 28.4 | 17382771.315 | 546.35 | 9023603.3331 | 0 | 0 | 70 | 1224138.825 | 0 | 0 | 27630513.4731
Non-Operational ¦ West Merredin to Kondinin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Operational ¦ West Merredin to Trayning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Operational ¦ Yilliminning to Kulin | 0 | 0 | 31.85 | 526039.6562 | 0 | 0 | 0 | 0 | 0 | 0 | 526039.6562
Non-Operational ¦ Katanning to Nyabing | 10.6 | 6487935.7725 | 663.25 | 10954342.2909 | 0 | 0 | 0 | 0 | 0 | 0 | 17442278.0634
Non-Operational ¦ Tambellup to Gnowangerup | 0 | 0 | 95.9 | 1583899.6241 | 455.2928 | 7962022.7603 | 0 | 0 | 0 | 0 | 9545922.3845
Non-Operational ¦ Katanning East to Katanning South | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 163.266 | 98133183.0706 | 11337.6866 | 183303853.8071 | 4200.3888 | 65446265.0242 | 6641.5846 | 104875219.9306 | 6023.555 | 112257407.7384 | 564015929.5709

## Section 4.6.3
Table 4-15 Length of Culverts Across the Network (km)
Network Group | Total length of MEA Culvert (km) by diameter (mm)
| 600 | 900 | 1200 | 1500 | 1800 | 2400 | 3000 | 3600 | Total
Metro | 5.8884 | 0 | 0.03 | 0.037 | 0.014 | 0.0318 | 0.013 | 0 | 6.0142
EGR | 13.4654 | 0.02996 | 0.1831 | 0.24341 | 1.8118 | 1.4136 | 0.32065 | 0.08878 | 17.5567
Midwest | 13.8835 | 0.075 | 0.9378 | 0.1563 | 0.0674 | 0.0172 | 0.0048 | 0 | 15.142
EBL | 5.909 | 1.2064 | 0.04466 | 0.06804 | 0.25218 | 0.05901 | 0.02294 | 0.0207 | 7.5829
LBL | 6.5063 | 0.05243 | 0.84308 | 0.11182 | 0.02336 | 0.83244 | 1.7084 | 0.04174 | 10.1196
SWM | 12.5703 | 0 | 0.0171 | 0.014 | 0.0137 | 0.0131 | 0.0359 | 0 | 12.6641
Collie | 43.3907 | 0.8422 | 0.8742 | 0.01 | 0.009 | 0.086 | 0.0037 | 0 | 45.2158
MR | 6.6261 | 0.9843 | 0.1159 | 0.063 | 0.0233 | 0.0202 | 0.021 | 0.0061 | 7.8599
Central | 8.2805 | 1.6732 | 10.1483 | 1.7706 | 8.6238 | 0.01822 | 0.04386 | 0.0036 | 30.5622
GSR | 14.5366 | 9.3435 | 0.4565 | 0.2264 | 0.2047 | 0.0243 | 0.0036 | 0.0037 | 24.7994
Lakes | 4.6413 | 3.5435 | 0.02318 | 0.0305 | 0.01342 | 0.00366 | 0.00732 | 0 | 8.2628
CBH Sidings | 0.0429 | 0.00366 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04656
Sidings & Other | 3.93 | 0 | 0 | 0.013 | 0 | 0 | 0 | 0 | 3.943
Non-Operational | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 139.6709 | 17.7541 | 13.6739 | 2.7441 | 11.0567 | 2.5195 | 2.1852 | 0.16462 | 189.769
Section 4.6.3 Supporting Information - Culvert Inventory by Route Section | [9 empty] | Section 4.6.3 Supporting Information - Culvert Replacement Cost by Route Section
| Total length of culverts by culvert diameter (metres) | [8 empty] | ($ '000s) (length x unit rate x location factor)
Route Section | 600 | 900 | 1200 | 1500 | 1800 | 2400 | 3000 | 3600 | Total | 600 | 900 | 1200 | 1500 | 1800 | 2400 | 3000 | 3600 | Total
Metro ¦ Kwinana West to Kwinana KBT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Kwinana North to Kwinana West | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Kwinana North to Kwinana | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Cockburn South to Kwinana North | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Cockburn East to Cockburn South | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Cockburn North to Cockburn East | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Cockburn North to Cockburn South | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Kenwick to Cockburn East | 297 | 0 | 10 | 0 | 0 | 15.8 | 0 | 0 | 322.8 | 266351.085 | 0 | 17936.1 | 0 | 0 | 56678.076 | 0 | 0 | 340965.261
Metro ¦ Forrestfield to Kenwick | 63 | 0 | 0 | 25 | 0 | 16 | 13 | 0 | 117 | 56498.715 | 0 | 0 | 56050.3125 | 0 | 57395.52 | 58292.325 | 0 | 228236.8725
Metro ¦ Forrestfield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Forrestfield South to Kewdale | 1560.4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1560.4096 | 1399383.0922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1399383.0922
Metro ¦ Woodbridge South to Forrestfield | 3187.8191 | 0 | 20 | 12 | 14 | 0 | 0 | 0 | 3233.8191 | 2858852.1193 | 0 | 35872.2 | 26904.15 | 37665.81 | 0 | 0 | 0 | 2959294.2793
Metro ¦ Woodbridge West to Woodbridge South | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metro ¦ Midland to Woodbridge South | 780.2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 780.2048 | 699691.5461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 699691.5461
EGR ¦ Midland to Millendon Junction | 188.9 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 207.9 | 186347.111 | 0 | 0 | 0 | 56229.6735 | 0 | 0 | 0 | 242576.7845
EGR ¦ Millendon Junction to Toodyay West | 3039.5 | 0 | 0 | 0 | 211.7 | 0 | 71.9 | 0 | 3323.1 | 2998422.6773 | 0 | 0 | 0 | 626516.9411 | 0 | 354641.5373 | 0 | 3979581.1556
EGR ¦ Toodyay West to Avon Yard | 4677.0191 | 15.7 | 0 | 0 | 45.4 | 0 | 51.3 | 0 | 4789.4191 | 4613811.5378 | 23231.7335 | 0 | 0 | 134359.3251 | 0 | 253033.5308 | 0 | 5024436.1272
EGR ¦ Avon Yard | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13990.158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13990.158
EGR ¦ Avon Yard to West Merredin | 1446.62 | 0 | 160.6 | 47.1 | 1458.3048 | 40.2 | 37.81 | 39.68 | 3230.3148 | 1686536.8638 | 0 | 374469.8958 | 137278.4254 | 5100478.5646 | 187468.1172 | 220403.2808 | 277564.7347 | 7984199.8824
EGR ¦ West Merredin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EGR ¦ West Merredin to Merredin | 7.2 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 16.2 | 8394.0948 | 0 | 0 | 0 | 0 | 41970.474 | 0 | 0 | 50364.5688
EGR ¦ Merredin to Southern Cross | 292.9 | 4.5 | 9 | 9.7 | 43.2 | 442.97 | 49.4 | 10.88 | 862.55 | 367743.8583 | 8474.8072 | 22599.486 | 30446.5298 | 162716.2992 | 2224643.1808 | 310115.169 | 81960.8026 | 3208700.1328
EGR ¦ Southern Cross to Koolyanobbing East | 1020.4748 | 0 | 4.5 | 4.5 | 20.7 | 178.7 | 52.2 | 4.88 | 1285.9548 | 1281233.6368 | 0 | 11299.743 | 14124.6787 | 77968.2267 | 897450.6996 | 327692.547 | 36761.8306 | 2646531.3624
EGR ¦ Koolyanobbing East to Mount Walton | 159.15 | 9.76 | 9 | 118.14 | 13.49 | 237.54 | 53.54 | 24.04 | 624.66 | 199817.122 | 18380.9153 | 22599.486 | 370819.8994 | 50811.1777 | 1192951.5343 | 336104.5779 | 181097.2145 | 2372581.9272
EGR ¦ Mount Walton to West Kalgoorlie West | 91.2 | 0 | 0 | 63.97 | 0 | 466.13 | 4.5 | 9.3 | 635.1 | 114504.0624 | 0 | 0 | 200790.1555 | 0 | 2340955.202 | 28249.3575 | 70058.4066 | 2754557.184
EGR ¦ West Kalgoorlie West to West Kalgoorlie | 120 | 0 | 0 | 0 | 0 | 17.4 | 0 | 0 | 137.4 | 150663.24 | 0 | 0 | 0 | 0 | 87384.6792 | 0 | 0 | 238047.9192
EGR ¦ West Kalgoorlie | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EGR ¦ West Kalgoorlie to Kalgoorlie | 1630.2096 | 0 | 0 | 0 | 0 | 21.66 | 0 | 0 | 1651.8696 | 2046772.1136 | 0 | 0 | 0 | 0 | 108778.8593 | 0 | 0 | 2155550.9729
EGR ¦ Kalgoorlie | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EGR ¦ Kalgoorlie to Parkeston (border) | 780.2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 780.2048 | 979568.1645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 979568.1645
Midwest ¦ Narngulu to Narngulu East | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Midwest ¦ Narngulu East to Mullewa | 3180.5143 | 57.6 | 909.2048 | 22 | 48.8 | 3.7 | 4.8 | 0 | 4226.6191 | 3707991.505 | 100729.1376 | 2119986.4168 | 64121.5575 | 170679.9276 | 17254.5282 | 27980.316 | 0 | 6208743.3887
Midwest ¦ Mullewa to Tilley Junction | 9292.8978 | 0 | 26.5 | 134.3 | 18.6 | 9.3 | 0 | 0 | 9481.5978 | 10834092.3535 | 0 | 61789.8645 | 391432.9624 | 65054.2347 | 43369.4898 | 0 | 0 | 11395738.9049
Midwest ¦ Tilley Junction to Tilley | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20985.237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20985.237
Midwest ¦ Tilley to Morawa | 51.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.8 | 60390.8487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60390.8487
Midwest ¦ Morawa to Perenjori | 1311.9648 | 17.4 | 2.1 | 0 | 0 | 4.2 | 0 | 0 | 1335.6648 | 1529549.5447 | 30428.5937 | 4896.5553 | 0 | 0 | 19586.2212 | 0 | 0 | 1584460.9149
Midwest ¦ Perenjori to Maya | 28.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.3 | 32993.456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32993.456
EBL ¦ West Kalgoorlie West to West Kalgoorlie South | 1560.4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1560.4096 | 2099074.6382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2099074.6382
EBL ¦ West Kalgoorlie to West Kalgoorlie South | 19.4 | 0 | 0 | 0 | 4.5 | 0 | 0 | 0 | 23.9 | 26097.0255 | 0 | 0 | 0 | 18160.3013 | 0 | 0 | 0 | 44257.3267
EBL ¦ West Kalgoorlie South to Hampton Intermodal Terminal | 50.4 | 0 | 0 | 0 | 31.4 | 0 | 0 | 0 | 81.8 | 67798.458 | 0 | 0 | 0 | 126718.5465 | 0 | 0 | 0 | 194517.0045
EBL ¦ Hampton Intermodal Terminal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBL ¦ Hampton Intermodal Terminal to Hampton | 63 | 0 | 0 | 0 | 4.5 | 0 | 0 | 0 | 67.5 | 84748.0725 | 0 | 0 | 0 | 18160.3013 | 0 | 0 | 0 | 102908.3737
EBL ¦ Hampton to Kambalda | 137.8 | 0 | 0 | 0 | 53.3 | 20.5 | 0 | 12 | 223.6 | 185369.5935 | 0 | 0 | 0 | 215098.6793 | 110307.015 | 0 | 96854.94 | 607630.2278
EBL ¦ Kambalda to Redmine | 65.6 | 0 | 0 | 0 | 86.7 | 13.1 | 0 | 0 | 165.4 | 88245.612 | 0 | 0 | 0 | 349888.4707 | 70488.873 | 0 | 0 | 508622.9558
EBL ¦ Kambalda to Salmon Gums | 2320.89 | 109.38 | 34.9 | 59.56 | 58.78 | 25.41 | 18.06 | 8.7 | 2635.68 | 3122078.6347 | 220708.1945 | 93895.4835 | 200301.3967 | 237213.8906 | 136726.8903 | 121472.2372 | 70219.8315 | 4202616.559
EBL ¦ Salmon Gums to Esperance | 1691.5048 | 1096.9848 | 9.76 | 8.48 | 13 | 0 | 4.88 | 0 | 2824.6096 | 2275424.9139 | 2213508.2264 | 26258.4504 | 28518.399 | 52463.0925 | 0 | 32823.063 | 0 | 4628996.1452
EBL ¦ Esperance to Esperance Wharf | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBL ¦ Esperance Wharf | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LBL ¦ Kalgoorlie to Menzies | 3426.9996 | 13.38 | 7.45 | 3.6 | 3.66 | 39.18 | 43.2 | 0 | 3537.4696 | 4610025.5057 | 26998.3145 | 20043.5917 | 12106.8675 | 14770.3784 | 210820.9194 | 290564.82 | 0 | 5185330.3972
LBL ¦ Menzies to Malcolm | 1878.5648 | 0 | 827.1048 | 85.86 | 19.7 | 9.76 | 854.6348 | 36.86 | 3712.4843 | 2527059.4288 | 0 | 2225255.1017 | 288748.7899 | 79501.7633 | 52516.9008 | 5748305.5667 | 297506.0907 | 11218893.6419
LBL ¦ Malcolm to Leonora | 1200.7348 | 39.05 | 8.53 | 22.36 | 0 | 783.5048 | 810.5848 | 4.88 | 2869.6443 | 1615237.4291 | 78795.5293 | 22949.24 | 75197.0992 | 0 | 4215906.0155 | 5452023.6148 | 39387.6756 | 11499496.6035
LBL ¦ Leonora | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SWM ¦ Kwinana to Mundijong Junction | 1780.0048 | 0 | 9.2 | 4 | 0 | 0 | 0 | 0 | 1793.2048 | 1915580.6221 | 0 | 19801.4544 | 10761.66 | 0 | 0 | 0 | 0 | 1946143.7365
SWM ¦ Mundijong Junction to Pinjarra | 510.6 | 0 | 7.9 | 0 | 3.7 | 3.6 | 18.7 | 0 | 544.5 | 549490.3596 | 0 | 17003.4228 | 0 | 11945.4426 | 15496.7904 | 100621.521 | 0 | 694557.5364
SWM ¦ Pinjarra to Pinjarra South | 17.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.3 | 18617.6718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18617.6718
SWM ¦ Pinjarra to Alumina Junction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SWM ¦ Alumina Junction to Pinjarra South | 2340.6143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340.6143 | 2518889.5659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2518889.5659
SWM ¦ Pinjarra South to Wagerup North | 2005.4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2005.4096 | 2158153.5806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2158153.5806
SWM ¦ Wagerup North to Wagerup South | 26.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.6 | 28626.0156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28626.0156
SWM ¦ Wagerup South to Brunswick North | 2291.9096 | 0 | 0 | 0 | 0 | 0 | 13.5 | 0 | 2305.4096 | 2466475.1396 | 0 | 0 | 0 | 0 | 0 | 72641.205 | 0 | 2539116.3446
SWM ¦ Brunswick North to Brunswick Junction | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 26904.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26904.15
SWM ¦ Brunswick Junction to Picton Junction | 1061.3248 | 0 | 0 | 10 | 0 | 9.5 | 3.7 | 0 | 1084.5248 | 1142161.6412 | 0 | 0 | 26904.15 | 0 | 40894.308 | 19909.071 | 0 | 1229869.1702
SWM ¦ Picton Junction to Picton East | 1560.4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1560.4096 | 1679259.7106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679259.7106
SWM ¦ Picton Junction to Bunbury Inner Harbour | 131.88 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 141.88 | 141924.7721 | 0 | 0 | 0 | 32284.98 | 0 | 0 | 0 | 174209.7521
SWM ¦ Picton Junction to Picton Container Terminal | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 30132.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30132.648
SWM ¦ Picton Container Terminal to Bunbury Terminal | 791.2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 791.2048 | 851467.6813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 851467.6813
SWM ¦ Picton Junction to Greenbushes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collie ¦ Brunswick North to Brunswick East | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 30132.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30132.648
Collie ¦ Brunswick Junction to Brunswick East | 2361.8143 | 780.2048 | 20 | 0 | 0 | 0 | 0 | 0 | 3162.0191 | 2541704.2851 | 1259444.7829 | 43046.64 | 0 | 0 | 0 | 0 | 0 | 3844195.708
Collie ¦ Brunswick East to Worsley | 34652.4055 | 62 | 15 | 0 | 0 | 40 | 0 | 0 | 34769.4055 | 37291740.5751 | 100083.438 | 32284.98 | 0 | 0 | 172186.56 | 0 | 0 | 37596295.5531
Collie ¦ Worsley to Worsley East | 803.7048 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 821.7048 | 864919.7563 | 0 | 38741.976 | 0 | 0 | 0 | 0 | 0 | 903661.7323
Collie ¦ Worsley East to Ewington Junction | 5234.7287 | 0 | 821.2048 | 10 | 9 | 46 | 3.7 | 0 | 6124.6334 | 5633437.0127 | 0 | 1767505.3226 | 26904.15 | 29056.482 | 198014.544 | 19909.071 | 0 | 7674826.5823
Collie ¦ Ewington Junction to Premier | 26.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.6 | 28626.0156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28626.0156
Collie ¦ Worsley East to Worsley North | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 17218.656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17218.656
Collie ¦ Worsley to Hamilton | 267.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267.4 | 287766.7884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287766.7884
MR ¦ Millendon Junction to Watheroo | 2749.2148 | 43.9 | 35.3 | 49.4 | 0 | 6.1 | 3 | 6.1 | 2893.0148 | 3205162.4269 | 76770.992 | 82308.7629 | 143982.0428 | 0 | 28446.6546 | 17487.6975 | 42669.9819 | 3596828.5585
MR ¦ Watheroo to Marchagee | 997.2148 | 12 | 0 | 0 | 3.6 | 3.6 | 0 | 0 | 1016.4148 | 1162599.3589 | 20985.237 | 0 | 0 | 12591.1422 | 16788.1896 | 0 | 0 | 1212963.9277
MR ¦ Marchagee to Dongara | 2636.0648 | 845.1048 | 12.2 | 7.9 | 10.2 | 6.9 | 18 | 0 | 3536.3696 | 3073246.8954 | 1477893.6716 | 28446.6546 | 23025.4684 | 35674.9029 | 32177.3634 | 104926.185 | 0 | 4775391.1413
MR ¦ Dongara to Narngulu | 168.6 | 16.1 | 20.4 | 5.7 | 9.5 | 3.6 | 0 | 0 | 223.9 | 196561.7199 | 28155.193 | 47566.5372 | 16613.3126 | 33226.6253 | 16788.1896 | 0 | 0 | 338911.5776
MR ¦ Narngulu to Geraldton | 75 | 67.2 | 48 | 0 | 0 | 0 | 0 | 0 | 190.2 | 87438.4875 | 117517.3272 | 111921.264 | 0 | 0 | 0 | 0 | 0 | 316877.0787
MR ¦ Dongara to Eneabba South | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central ¦ Avon Yard to Goomalling | 780.61 | 88.6 | 22.2 | 9.7 | 11.9 | 0 | 3.6 | 0 | 916.61 | 840065.9413 | 143022.4614 | 47781.7704 | 26097.0255 | 38419.1262 | 0 | 19370.988 | 0 | 1114757.3128
Central ¦ Goomalling to McLevie | 921.8 | 911.3 | 209.36 | 80.12 | 8594.3 | 7.32 | 18.36 | 0 | 10742.56 | 992009.8188 | 1471065.1137 | 450612.2275 | 215556.0498 | 27746680.3614 | 31510.1405 | 98792.0388 | 0 | 31006225.7505
Central ¦ Goomalling to Amery | 561.7 | 0 | 0 | 20.8 | 0 | 10.9 | 3.6 | 0 | 597 | 604482.4422 | 0 | 0 | 55960.632 | 0 | 46920.8376 | 19370.988 | 0 | 726734.8998
Central ¦ Amery to Mukinbudin | 1261.66 | 503.4 | 9880.3 | 1593.1096 | 11.5 | 0 | 0 | 3.6 | 13253.5696 | 1357755.5956 | 812612.9466 | 21265685.8596 | 4286125.847 | 37127.727 | 0 | 0 | 23245.1856 | 27782553.1613
Central ¦ Amery to Burakin | 923.14 | 11 | 7.2 | 10.8 | 2.6 | 0 | 0 | 0 | 954.74 | 993451.8812 | 17756.739 | 15496.7904 | 29056.482 | 8394.0948 | 0 | 0 | 0 | 1064155.9874
Central ¦ Burakin to Kalannie | 245.12 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 248.12 | 263789.8099 | 0 | 0 | 8071.245 | 0 | 0 | 0 | 0 | 271861.0549
Central ¦ Burakin to Beacon | 539.11 | 127.28 | 14.64 | 3 | 3.5 | 0 | 0 | 0 | 687.53 | 580171.8523 | 205461.6127 | 31510.1405 | 8071.245 | 11299.743 | 0 | 0 | 0 | 836514.5935
Central ¦ Toodyay West to Miling | 3047.3248 | 31.66 | 14.64 | 50.1 | 0 | 0 | 18.3 | 0 | 3162.0248 | 3279427.3172 | 51107.1233 | 31510.1405 | 134789.7915 | 0 | 0 | 98469.189 | 0 | 3595303.5615
GSR ¦ Avon Yard to York | 2798.3943 | 298.21 | 280.24 | 87.5 | 46 | 0 | 0 | 0 | 3510.3443 | 3262498.2405 | 521500.6271 | 653433.6463 | 255028.9219 | 160886.817 | 0 | 0 | 0 | 4853348.2528
GSR ¦ York to Brookton | 4237.5239 | 8887 | 105.9 | 98.1 | 146.7 | 6 | 0 | 0 | 13481.2239 | 4940302.3967 | 15541316.7682 | 246926.2887 | 285923.8541 | 513089.0446 | 27980.316 | 0 | 0 | 21555538.6685
GSR ¦ Brookton to Narrogin | 3442.8343 | 20 | 38.16 | 2.1 | 12 | 3.6 | 3.6 | 0 | 3522.2943 | 4013816.3589 | 34975.395 | 88977.4049 | 6120.6941 | 41970.474 | 16788.1896 | 20985.237 | 0 | 4223633.7535
GSR ¦ Narrogin to Wagin | 458.32 | 19.2 | 6.3 | 4.2 | 0 | 6.1 | 0 | 0 | 494.12 | 534330.7679 | 33576.3792 | 14689.6659 | 12241.3882 | 0 | 28446.6546 | 0 | 0 | 623284.8558
GSR ¦ Wagin to Wagin South | 9.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.7 | 11308.711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11308.711
GSR ¦ Wagin South to Katanning | 517.22 | 25.3 | 11.4 | 8.4 | 0 | 0 | 0 | 0 | 562.32 | 602999.1267 | 44243.8747 | 26581.3002 | 24482.7765 | 0 | 0 | 0 | 0 | 698307.0781
GSR ¦ Katanning to Tambellup | 1170.1248 | 7.2 | 7.2 | 6.3 | 0 | 0 | 0 | 3.7 | 1194.5248 | 1364185.8772 | 12591.1422 | 16788.1896 | 18362.0824 | 0 | 0 | 0 | 25881.7923 | 1437809.0837
GSR ¦ Tambellup to Redmond | 1230 | 39 | 7.3 | 10 | 0 | 8.6 | 0 | 0 | 1294.9 | 1433991.195 | 68202.0203 | 17021.3589 | 29146.1625 | 0 | 40105.1196 | 0 | 0 | 1588465.8563
GSR ¦ Redmond to Albany | 672.53 | 47.6 | 0 | 9.8 | 0 | 0 | 0 | 0 | 729.93 | 784066.7466 | 83241.4401 | 0 | 28563.2393 | 0 | 0 | 0 | 0 | 895871.426
Lakes ¦ Wagin East to Wagin South | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lakes ¦ Wagin to Lake Grace | 2914.6896 | 2614.3443 | 19.52 | 7.3 | 13.42 | 0 | 7.32 | 0 | 5576.5939 | 3398080.6178 | 4571886.2882 | 45514.6474 | 21276.6986 | 46936.9801 | 0 | 42669.9819 | 0 | 8126365.214
Lakes ¦ Lake Grace to Newdegate | 495.82 | 895.0548 | 3.66 | 10.6 | 0 | 0 | 0 | 0 | 1405.1348 | 578050.0116 | 1565244.7206 | 8533.9964 | 30894.9323 | 0 | 0 | 0 | 0 | 2182723.6609
Lakes ¦ Lake Grace to Hyden | 1230.78 | 34.06 | 0 | 12.6 | 0 | 3.66 | 0 | 0 | 1281.1 | 1434900.5553 | 59563.0977 | 0 | 36724.1648 | 0 | 17067.9928 | 0 | 0 | 1548255.8105
CBH Sidings ¦ CBH SG Sidings (all) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CBH Sidings ¦ CBH NG Sidings (all) | 42.9 | 3.66 | 0 | 0 | 0 | 0 | 0 | 0 | 46.56 | 47817.6426 | 6400.4973 | 0 | 0 | 0 | 0 | 0 | 0 | 54218.1399
Sidings & Other ¦ Cockburn North to Robb Jetty (SG) | 12 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 25 | 10761.66 | 0 | 0 | 29146.1625 | 0 | 0 | 0 | 0 | 39907.8225
Sidings & Other ¦ SG Siding - Esperance Industrial Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ SG Siding - West Kalgoorlie Industrial Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ SG Siding - Kewdale North Grid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ SG Siding - Kewdale BP Loading Depot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ Cockburn North to Robb Jetty (NG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ Redmond to Mirrambeena | 3901.0239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3901.0239 | 4547995.0495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4547995.0495
Sidings & Other ¦ NG Siding - Kwinana to Kwinana Alcoa | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ NG Siding - Kwinana to Kwinana West | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ NG Siding - Kwinana West to Kwinana KBT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ NG Siding - Extension Hill Siding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ NG Siding - Tilley Siding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ DG Siding - Kwinana West to Kwinana FPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidings & Other ¦ DG Siding - Kwinana FPA to Kwinana CBH | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 15245.685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15245.685
Non-Operational ¦ Greenbushes to Lambert | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Operational ¦ Boyanup to Capel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Operational ¦ York to Quairading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Operational ¦ Narrogin to West Merredin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Operational ¦ West Merredin to Kondinin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Operational ¦ West Merredin to Trayning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Operational ¦ Yilliminning to Kulin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Operational ¦ Katanning to Nyabing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Operational ¦ Tambellup to Gnowangerup | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Operational ¦ Katanning East to Katanning South | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 139670.9225 | 17754.1334 | 13673.8743 | 2744.0996 | 11056.6548 | 2519.5348 | 2185.1896 | 164.62 | 189769.0289 | 156656086.9394 | 31046774.3413 | 30210742.0563 | 7688171.4022 | 36355839.5469 | 12804665.0458 | 14199855.1162 | 1246808.4865 | 290193942.9346

## Section 6.2.5
Right of Way Remaining Life (%) and Depreciated Optimised Replacement Cost ($ million)
Network Group | ORC ($ million) | Right of Way activity |  |  |  |  | DORC ($million)
|  | Clearing and Grubbing | Cutting and Embankments | Formation | Access Roads | Subtotal
|  | ($ million) | ($ million) | ($ million) | ($ million) | ($ million)
Alternative A
ORC |  | 116.8 | 31.8 | 2755.2 | 1047.7 | 3951.4
Metro | 88.9 | 100% | - | 100% | 40% | -8.3 | 80.6
EGR | 959.5 | 100% | - | 100% | 58% | -64.2 | 895.3
Midwest | 385 | 100% | 100% | 100% | 56% | -26.3 | 358.7
EBL | 595.3 | 100% | - | 100% | 66% | -49.9 | 545.4
LBL | 118.5 | 100% | - | 100% | 71% | -17.5 | 101
SWM | 250.6 | 100% | - | 100% | 44% | -31.3 | 219.3
Collie | 25 | 100% | - | 100% | 55% | -5.9 | 19.1
MR | 221.8 | 100% | - | 100% | 57% | -49.4 | 172.4
Central | 249.5 | 100% | - | 100% | 50% | -63.3 | 186.2
GSR | 584.7 | 100% | - | 100% | 65% | -30 | 554.7
Lakes | 108.2 | 100% | - | 100% | 64% | -19.9 | 88.3
CBH Sidings | 38.7 | 100% | - | 100% | 47% | -9.9 | 28.8
Sidings & Other | 14.4 | 100% | - | 100% | 69% | -2.6 | 11.8
Non-Operational | 311.3 | 100% | - | 100% | 0% | -160.3 | 151
Subtotal |  | 0 | 0 | 0 | -538.8 | -538.8 | 3412.6
TOTAL | 3951.4 | 116.8 | 31.8 | 2755.2 | 508.9 | 3412.6